## Slide 1
Gravity Project Roadmap (Task 5: HL7 FHIR Integration)
Jun 20 – Aug 20
Sep 20 – Nov 20
Dec 19 – Jan 20
Feb 20 – May 20
Sep 19 - Nov 19
Community Engagement
Connectathon Testing
FHIR IG/Ballot
Draft SDOH Implementation Guide Development for Q2 2020 Testing
IG revisions based on Community Feedback and Additional Development
IG revisions based on Connectathon Testing, Development
Comment Only IG Ballot Reconciliation
Sept STU Ballot Reconciliation
HL7 Connectathon 23, Sydney, UC 1 (Feb)
HL7 Connectathon 24, San Antonio, UC 1, 2 (May)
HL7 Connectathon 25, Baltimore, UC 1, 2 (Sept)
https://confluence.hl7.org/display/GRAV/Gravity+SDOH+FHIR+IG
HIMSS Demonstration, Orlando, UC 1 (Mar)
HL7 STU Ballot (Aug to Dec)
V0.0.2 (Jan 30, 2020)
V0.0.3 (Feb 28, 2020)
V0.0.4 (April 15, 2020)
V0.0.5 (June 15, 2020)
V0.1.0 (July 15, 2020)
UC1
UC1-2
UC1-2
V0.0.1 (Dec 12, 2019)
Community Review
Kick-off
Community Review
Community Review
V1.0.0
Notes: Reuse:
C-CDA on FHIR: Care Plan, CCD, H&P, Progress Note, Referral Note, Consultation Note
US Core: Patient, Practitioner, PractitionerRole, Organization, Coverage
Da Vinci: CDex
FHIR: Goal, Questionnaire, QuestionnaireResponse, Observation, Consent, Bundle(Document), Bundle(Transaction), CarePlan
Profile:
Food Insecurity Observation
Food Security Observation